Work Package 6 Interim Report

The first visit of Work Package 6 provided intensive training for research methodologies at the beginning of the HEIM project.

The Roma Education Fund representatives attending the University of Sussex for intensive training were:

|  | Name | Secondment Dates | Days |
| --- | --- | --- | --- |
| 1 | Mihaela Velicu | 21st June 2015 - 17th July 2015, 1st – 4th November 2015 | 31 |
| 2 | Gabriela Petre | 21st June 2015 - 17th July 2015, 1st – 4th November 2015 | 31 |
| 3 | Dănuț Dumitru | 21st June 2015 - 17th July 2015 (27 days) | 27 |
| 4 | Máté Dezső | 21st June 2015 - 17th July 2015, 1st – 4th November 2015 | 31 |
| 5 | Szilvia Pallaghy | 21st June 2015 - 17th July 2015, 1st – 4th November 2015 | 31 |
| 6 | Radoslav Kuzmanov | 21st June 2015 - 17th July 2015, 1st – 4th November 2015 | 31 |
| 7 | Marsela Taho | 21st June 2015 - 17th July 2015, 1st – 4th November 2015 | 31 |
| 8 | Ljubica Tomic | 21st June 2015 - 17th July 2015, 1st – 4th November 2015 | 31 |
| 9 | Dragana Radoman | 5th - 19th July 2015 (15 days) 7th - 23rd March 2016 (15 days). | 30 |
| 10 | Albena Velcheva | 21st June 2015 - 17th July 2015 (27 days) | 27 |
|  |  |  | 301 |

One attendee (Dragana Radoman) was delayed in arriving due to visa processing issues, resulting in revised secondment dates. She completed her 30 days in March 2016.

Two attendees (Dănuț Dumitru and Albena Velcheva) could not make the November part of the event due to personal circumstances.

Workshop content

The Training Programme for colleagues from the Roma Education Fund (REF) started on Monday 22nd June 2015 until 17th July 2015, with a follow-up event on the 1st to 4th November 2015.

During this time, REF colleagues followed an intensive programme of training in qualitative and quantitative research training and theoretical work on social inclusion to support them in their policy work in promoting educational opportunities for the Roma community in Europe.

The programme for the secondment is available on: http://www.sussex.ac.uk/doctoralschool/internal/newsandevents/heimresearchtraining/heimprogramme

Evaluation

An evaluation of the training was undertaken in November 2015 by Professor John Pryor with the attendees, the report is attached as annex A.

Feedback to EC Project Officer

- The funds provided for the secondment were not sufficient to cover the full-costs of the training.  The programme was only possible due to in-kind contributions from the University of Sussex’s Researcher Development Programme.

- The implementation of the secondments was challenging due to the changing nature of the business needs of the Roma Education Fund, personal circumstances of individuals and the length of the secondment.  Greater flexibility on how secondments can be structured would be a welcome improvement to the scheme.

Paul Roberts

Work package 6 co-ordinator

27 April 2016

Annex A: Participant Evaluation of Work Package 6

This report is compiled from comments written on posters by subgroups of participants and shared with the whole group as well as plenary discussion of the work package.

Overall the programme was seen as very good. In particular the work on quantitative and qualitative research was seen as useful by all participants. The focus groups where they were research subjects were also useful in extending their understanding of these as a research method. The opportunities to interact with others in the group, for those who work in other offices and for those doing a PhD and particularly, students those from other countries. Encountering Roma from a different backgrounds was seen as valuable. Sessions where there was interaction with students and faculty from Sussex were also considered a highlight: they felt they had learned a lot from the international mix but also something about British culture. Opportunities for this came from both the academic and the social events. The ‘experience of being in a high ranked western university’ was also seen as important and new for them. Those studying for a PhD thought that the programme and the interaction with a variety of people had enabled them to learn about different education systems and thus broadened their knowledge. In particular participants felt that they had developed a much better understanding of the concept of educational inclusion by considering it and experiencing from different perspectives.

Participants agreed that they were now applying the knowledge and experience that they had gained from the work package in their everyday work. It had enabled them to read reports from grantees and other partners in a much more informed and critical manner, asking questions about how the data were collected and reported. This involved more and deeper thinking about what was in these reports. It had also given them skills to prepare better reports and proposals themselves – not only including data but also an analysis of the data. Those doing PhDs said that they were incorporating the ideas into their research and this had influenced the design of their projects, which had developed well since they started the programme. Some things they had learnt but were not yet using, for example the zotero computer package.

Participants also identified further needs and suggested activities which might be have been in the 2015 secondment or could be included in the one to take place in 2017. Among these were intensive English classes and some sessions on academic writing as well as some addressing particular software SPSS and Atlas Ti were mentioned. They would welcome having a research task to accomplish themselves during any future secondment. Those not doing a PhD would value input on writing research proposals and applying for a PhD. On the social side participants would have enjoyed more outings and visits with their hosts.